## Slide 1
2024-2027
GWDB Strategic Plan
Implementation and Execution
GWDB Executive Committee Meeting | July 17, 2024

## Slide 2
Strategic Plan
Over the course of 2023, the GWDB worked diligently to write and submit the WIOA State Plan to the US Department of Labor and Education to secure millions in federal funding for workforce development. After submitting the WIOA State Plan on March 4, 2024 GWDB Chair Hugh Anderson and Vice Chair Ken Evans created a task force of business Board members representing various sectors and industries and State agencies to draft the first GWDB strategic plan. The vision for the strategic plan was to build upon the goals set forth in the WIOA State Plan and add emphasis on private and public sector alignment and collaboration for workforce development. The GWDB Strategic Plan is intended to be much more concise and actionable than the WIOA State Plan. Special thanks to the GWDB Strategic Plan Task Force Members: GWDB Vice Chair Ken Evans, Nancy Olsen, Edward Estipona, Ryan Woodward, Ken Goodrich, and Scott Hammond.
GWDB
The Governor's Workforce Development Board (GWDB) serves as the primary convener for industry, labor, and government leaders dedicated to innovating workforce development for the State of Nevada through examining the statewide workforce development system, creating the Workforce Innovation and Opportunity Act (WIOA) State Plan, and recommending workforce development policy improvements to the Governor’s Office, Office of Workforce Innovation (OWINN), Nevada Legislature, and all relevant workforce stakeholders. The GWDB is codified by NRS 232.935 and administered by OWINN. The GWDB is led by Chair Hugh Anderson and Vice Chair Ken Evans. The GWDB’s 33 members are Governor appointed and a majority represent businesses from various industry sectors, along with state and local elected officials, organized labor representatives, and administrators of the State’s WIOA core programs.
Background
2 | GWDB Strategic Plan

## Slide 3
Charge
To gather perspectives from industry, labor, and government partners; craft policy recommendations that support the Governor’s vision; and deploy these recommendations to the Governor’s Office, Nevada Legislature, state agencies, and local workforce development boards.
Mission
The GWDB will mitigate workforce and learning barriers for Nevadans with low labor force participation and high unemployment rates (who are defined as “underserved populations”), promote awareness and engagement of the Nevada’s businesses with the public workforce system, and align the Nevada workforce system among education, economic development, and workforce development private and public sector partners.
Charge + Mission
3 | GWDB Strategic Plan
Population
Engagement
Alignment

## Slide 4
Goal 1: Population
The GWDB will mitigate workforce and learning barriers for underserved Nevadans (those who have low labor force participation and high unemployment rates).
Goal 2: Engagement
The GWDB will promote awareness and engagement of Nevada’s businesses with the public workforce system.
Goal 3: Alignment
The GWDB will align the Nevada workforce system among education, economic development, and workforce development private and public sector partners.
4 | GWDB Strategic Plan

## Slide 5
Goal 1: Population - The GWDB will mitigate workforce and learning barriers for underserved Nevadans (those who have low labor force participation and high unemployment rates).
Strategy 1: Actively promote and market public workforce system services and career opportunities to underserved communities to increase awareness and access.
AWARENESS
Strategy 3: Champion the public and nonprofit workforce staff that provide these services and remove duplication of services to best allocate resources.
SUPPLY
Action Item: Create a quarterly or annual shared calendar of workforce events among all partners on the Execution Team to track which events are being held in specific communities, which industries will be represented, which supportive services will be available, and maintain a stream of constant communication among all Execution Team partners so there is not duplication of effort.
Measurement & Time Frame: __ number of job fairs, __ number of resource fairs, __ number of new outreach centers established
Execution Team: OWINN, DETR, Workforce Connections, Nevadaworks, DWSS, nonprofits, GWDB, chambers of commerce, Business & Industry, private businesses, trade associations
Action Item: Track the effectiveness of job fairs, resource fairs, new outreach and training centers, etc. by surveying attendees or clients on whether the event or center was effective for serving their needs. Display metrics on the GWDB workforce development dashboard (mentioned in Goal 3).
Measurement & Time Frame: __ number of people hired after a job fair, __ number of people on public assistance after a resource fair, __ number of clients who entered a training program after attending a job/resource fair or using a job center.
Execution Team: OWINN, DETR, Workforce Connections, Nevadaworks, DWSS, GWDB
Action Item: Provide better job opportunities to client-assisting agencies to incentivize passionate workers to stay in their roles and attract more people into the field.
Measurement & Time Frame: __ increase in case workers, ___ increase in partnerships
Execution Team: State DHRM, OWINN, DETR, Workforce Connections, Nevadaworks, DWSS, nonprofits
Action Item: Utilize the jobseeker resources asset map to determine which organizations are providing these resources and where services can be streamlined.
Measurement & Time Frame: Once asset map developed, create crosswalk of similar services by ___. Begin conversations of streamlining resources by __.
Execution Team: OWINN, GWDB
Strategy 2: Streamline application to apply for workforce and supportive services and develop asset map for jobseekers of workforce and supportive services resources available across the state.
ACCESS
Action Item: Develop a working group with all WIOA Titles and client-assisting agencies to develop a better application and referral system, creating a “no-wrong door” approach.
Measurement & Time Frame: Increase number of referrals by ___ %
Execution Team: DWSS, DETR, Workforce Connections, Nevadaworks, Business & Industry, NDVS, NDOC, Adult Education, Vocational Rehabilitation
Action Item: Create an asset map jobseekers can use to find workforce and supportive services that will help propel them into employment.
Measurement & Time Frame: Create asset map by _
Execution Team: OWINN, GWDB
Population
1A
2A
3A
4A
5A
6A
4 | GWDB Strategic Plan

## Slide 6
Action Item 1A: Create shared calendar of workforce events.
Measurement: _ job fairs, _ job centers, etc.
Time Frame:
Feb 2025
Execution Team:
OWINN, GWDB, DETR, WC, DWSS, NVWorks, nonprofits, chambers of commerce, Dept. of B&I, private businesses, trade associations
Main page
Population
Strategy 1: Awareness of public workforce system to underserved communities.
5 | GWDB Strategic Plan
Action Item 2A: Track the effectiveness of outreach. Display metrics on dashboard.
Measurement: _ hires after job fair, _ clients placed in training after visiting job centers, etc.
Time Frame:
Sep 2025
Execution Team:
OWINN, GWDB,
DETR, WC, NVWorks, DWSS
Action Item 3A: Develop better application and referral system.
Measurement: _ % increase in referrals, _ reduced time for client to receive assistance
Time Frame:
Dec 2024
Execution Team:
DWSS, DETR, WC, NVWorks, Dept. of B&I, NDVS, NDOC, Adult Education, Vocational Rehabilitation
Strategy 2: Streamline workforce and supportive services application and develop asset map for job seekers.
Action Item 4A: Create workforce and supportive services asset map for job seekers.
Measurement: Complete asset map by _.
Time Frame:
Feb 2025
Execution Team:
OWINN, GWDB
Action Item 5A: Provide better career opportunities to client-assisting staff.
Measurement: _ increase in case workers, etc.
Time Frame:
Jun 2026
Execution Team:
State DHRM, OWINN, DETR, WC, NVWorks, DWSS, nonprofits
Strategy 3: Champion public and nonprofit workforce staff and remove duplication of services.
Action Item 6A: Assess where services can be streamlined.
Measurement: Create crosswalk of similar services by _, begin resource streamlining by _
Time Frame:
May 2025
Execution Team:
OWINN, GWDB

## Slide 7
6 | GWDB Strategic Plan
Goal 2: Engagement - The GWDB will promote awareness and engagement of Nevada’s businesses with the public workforce system.
Strategy 2: Ensure that all job training programs provide relevant coursework that satisfies the needed skillsets of employers.
EFFECTIVENESS
Strategy 1: Make employers aware of public workforce training resources and funding opportunities.
AWARENESS
Action Item: Launch a “Did you Know?” campaign in conjunction with chambers of commerce, regional and state economic development agencies, trade associations, and other business organizations to spread the word about workforce resources available to employers
Execution Team: GWDB, OWINN, Workforce Connections, Nevadaworks, DETR, chambers of commerce, regional and state economic development agencies, trade associations, Business & Industry
Measurement & Time Frame: ___ number of campaign posts on social media, ___ number of increased website traffic, ___ number of direct employer engagements
Action Item: Create an in-demand skills list similar to the in-demand occupations list (created by GOED) by surveying employers of their most needed skills for their workforce. Once the in-demand skills list is created, meet with K-12 career and technical education instructors and postsecondary training providers to confirm that their courses provide the in-demand skills of each industry.
Measurement & Time Frame: Task the GWDB and OWINN to work with GOED and produce the in-demand skills list by ___. Disseminate list to K-12 career and technical education instructors training providers and evaluate the match of skills provided by each training program to the in-demand skills for each industry by ___. Update the in-demand skills list semi-annually to keep current with current workforce trends. Meet with K-12 and postsecondary providers annually.
Execution Team: GWDB, OWINN, GOED, NDE, school district CTE coordinators, NSHE institutions, training providers
Action Item: Connect commonly touched business departments within the State to cross-promote workforce services.
Measurement & Time Frame: Develop consistent branding of workforce services promotion for the commonly touched business departments.
Execution Team: Department of Taxation, Secretary of State, DETR, Business & Industry
Action Item: Ensure small businesses are a priority to assist with public workforce training resources and funding opportunities by attending small business events and partnering with small business advocacy groups to demonstrate all available resources.
Measurement & Time Frame: Develop consistent branding of workforce services promotion for the commonly touched business departments.
Execution Team: Nonprofits, DETR, Business & Industry, GOED, Secretary of State, OWINN, GWDB
Engagement
1B
2B
3B
4B

## Slide 8
Action Item 1B: Launch “Did you Know?” campaign.
Measurement: _ % increased website traffic, _ direct employer engagements, etc.
Time Frame:
Dec 2024
Execution Team:
GWDB, OWINN, WC, NVWorks, DETR, chambers of commerce, GOED, RDAs, trade associations, Dept. of B&I
Main page
Engagement
Strategy 1: Make employers aware of public workforce training resources and funding opportunities.
7 | GWDB Strategic Plan
Action Item 2B: Cross promote workforce services with common business-serving agencies.
Measurement: Develop consistent branding by _.
Time Frame:
Sep 2025
Execution Team:
OWINN, Dept. of Taxation, Secretary of State, DETR, Dept. of B&I
Action Item 3B: Ensure small businesses are a priority for public workforce system resources.
Measurement: Attend _ small business events. Partner with _ small business advocacy groups.
Time Frame:
Sep 2025
Execution Team:
Nonprofits, DETR, Dept. of B&I, GOED, Secretary of State, OWINN, GWDB
Strategy 2: Ensure job training coursework meets employer needs.
Action Item 4B: Create in-demand skills list. Confirm with training providers that their courses teach the in-demand skills.
Measurement: Produce in-demand skill list by _. Work with _ training providers by _ .
Time Frame:
Feb 2025
Execution Team:
GWDB, OWINN, GOED, NDE, CTE coordinators, NSHE institutions, training providers

## Slide 9
Goal 3: Alignment - The GWDB will align the Nevada workforce system among education, economic development, and workforce development private and public sector partners.
Strategy 2: Determine where there are gaps in workforce development resources and trainings at the local, regional, and statewide level, then partner with education, economic development, and workforce development to create new, innovative programs that meet the emerging workforce needs of businesses.
EFFECTIVENESS
Strategy 1: Identify all workforce development private and public partners at the local, regional, and statewide levels and enumerate the specific services they provide.
AWARENESS
Action Item: Connect with current partners and utilize connections to create an inventory of all workforce development partners in the state.
Execution Team: GWDB, OWINN
Measurement & Time Frame: Create list of partners by ___ .
Action Item: Use the jobseeker and workforce system asset maps to develop a gap analysis and conduct stakeholder engagement among partners to see where their shortfalls are and how the GWDB could convene partners to mitigate those gaps.
Measurement & Time Frame: Conduct a gap analysis using the asset maps by ___ . Start conducting stakeholder engagement meetings on ___ .
Execution Team: GWDB, OWINN,
Action Item: Create an asset map of the services provided by each of the workforce development partners on the inventory for workforce system partners.
Measurement & Time Frame: Create workforce system asset map by ___
Execution Team: GWDB, OWINN
Action Item: Pair the gap analysis with the in-demand skills list to develop new programming that meets the emerging workforce needs of businesses, leveraging connections with education, economic development, and workforce development.
Measurement & Time Frame: Analyze the gap analysis and in-demand skills list by __. Begin to develop working groups with targeted education, economic development, and workforce development to design new programs by __.
Execution Team: GWDB, OWINN, GOED, regional economic development authorities, NSHE institutions, NDE, school district CTE coordinators, training providers, nonprofits, Business & Industry, DETR, Workforce Connections, Nevadaworks
Strategy 3: Develop a comprehensive workforce development dashboard housed within the GWDB that displays metrics from cross-agency partners to inform real-time, data-driven decisions for policymakers.
PERFORMANCE
Action Item: Approach relevant local, regional, and state agencies to determine which metrics would be appropriate to display in the GWDB workforce development dashboard. Develop data-sharing agreements with data-sharing partners.
Measurement & Time Frame: Develop list of potential data-sharing partners by ___. Meet with data-sharing partners by __. Develop data-sharing agreements with partners by ___.
Execution Team: GWDB, OWINN, DETR, Workforce Connections, Nevadworks, DWSS, Adult Education, Vocational Rehabilitation, NDE, Business & Industry, NSHE Institutions, training providers, nonprofits, GOED, chambers of commerce, regional economic development authorities,
Action Item: Create the GWDB workforce development dashboard and analyze data updates at GWDB Full Board meetings with relevant stakeholders as guest speakers. Use dashboard to monitor continuous improvement for the workforce development system.
Measurement & Time Frame: Once data-sharing agreements in place, OWINN develop dashboard by ___.
Execution Team: OWINN, GWDB
Alignment
1C
2C
3C
4C
5C
6C
8 | GWDB Strategic Plan

## Slide 10
Action Item 1C: Create inventory of all workforce partners in the State.
Measurement: Complete inventory by _.
Time Frame:
Dec 2024
Execution Team:
OWINN, GWDB
Main page
Alignment
Strategy 1: Identify services provided by all workforce partners.
9 | GWDB Strategic Plan
Action Item 2C: Develop asset map of workforce partner services.
Measurement: Complete asset map by _.
Time Frame:
May 2025
Execution Team:
OWINN, GWDB
Action Item 3C: Produce gap analysis of services and conduct stakeholder engagement to decrease gaps.
Measurement: Complete gap analysis by _. Start stakeholder engagement by _.
Time Frame:
Sep 2025
Execution Team:
OWINN, GWDB
Strategy 2: Determine gaps in services then create new programs to meet business needs.
Action Item 4C: Design new programming to meet business workforce needs.
Measurement: Analyze gap analysis and in-demand skills list by _. Convene work groups by _.
Time Frame:
Jun 2026
Execution Team:
OWINN, GWDB, GOED, RDAs, NSHE, NDE, WC, NVWorks, CTE coordinators, training providers, nonprofits, Dept. of B&I, DETR.
Action Item 5C: Approach partners to determine dashboard metrics. Develop data-sharing agreements.
Measurement: Develop list of data-sharing partners by_. Meet with partners by _. Finalize agreements by _.
Time Frame:
Feb 2025
Execution Team:
GWDB, OWINN, DETR, WC, NVWorks, Adult Education, NDE, Vocational Rehabilitation, Dept. of B&I, NSHE, GOED, RDAs, chambers of commerce, training providers, nonprofits
Strategy 3: Develop comprehensive GWDB workforce dashboard.
Action Item 6C: Create the GWDB workforce dashboard. Monitor continuous improvement at GWDB meetings.
Measurement: Complete dashboard by _.
Time Frame:
May 2025
Execution Team:
OWINN, GWDB

## Slide 11
Dec 2024
3A | Application & referral system
1B | “Did you Know?” campaign
1C | Workforce inventory
Feb 2025
1A | Shared calendar
4A | Jobseekers asset map
5C | Data-sharing agreements for dashboard
Sep 2025
Jun 2026
10 | GWDB Strategic Plan
4B | In-Demand skills list
May 2025
6A | Streamline services
6C | Create dashboard
2C | Ecosystem asset map
3B | Priority for small businesses
2A | Outreach metrics
2B | Cross promote workforce services to business agencies
3C | Gap analysis
5A | Enhance career opportunities for staff
4C | New programming

## Slide 12
Performance Scorecard
11 | GWDB Strategic Plan
2024-2027 GWDB Strategic Plan Performance Scorecard |  |  |  |  |  | 
Unit | Action Item | Time Period | Execution Team | Measurement | Status | Notes
3A | Application & referral system | Dec 2024 | DWSS, DETR, WC, NVWorks, Dept. of B&I, NDVS, NDOC, Adult Education, Vocational Rehabilitation | _ % increase in referrals, _ reduced time for client to receive assistance |  | 
1B | “Did you Know?” campaign | Dec 2024 | GWDB, OWINN, WC, NVWorks, DETR, chambers of commerce, GOED, RDAs, trade associations, Dept. of B&I | _ % increased website traffic, _ direct employer engagements, etc. |  | 
1C | Workforce inventory | Dec 2024 | OWINN, GWDB | Complete inventory by _. |  | In-progress with LVGEA
1A | Shared calendar | Feb 2025 | OWINN, GWDB, DETR, WC, DWSS, NVWorks, nonprofits, chambers of commerce, Dept. of B&I, private businesses, trade associations | _ job fairs, _ job centers, etc. |  | 
4A | Jobseekers asset map | Feb 2025 | OWINN, GWDB | Complete asset map by _. |  | Assign to Barriers Subcommittee
4B | In-Demand skills list | Feb 2025 | GWDB, OWINN, GOED, NDE, CTE coordinators, NSHE institutions, training providers | Produce in-demand skill list by _. Work with _ training providers by _ . |  | Began meeting with GOED
5C | Data-sharing agreements for dashboard | Feb 2025 | GWDB, OWINN, DETR, WC, NVWorks, Adult Education, NDE, Vocational Rehabilitation, Dept. of B&I, NSHE, GOED, RDAs, chambers of commerce, training providers, nonprofits | Develop list of data-sharing partners by_. Meet with partners by _. Finalize agreements by _. |  | 
6A | Streamline services | May 2025 | OWINN, GWDB | Create crosswalk of similar services by _, begin resource streamlining by _ |  | 

## Slide 13
12 | GWDB Strategic Plan
Performance Scorecard Cont.
2024-2027 GWDB Strategic Plan Performance Scorecard |  |  |  |  |  | 
Unit | Action Item | Time Period | Execution Team | Measurement | Status | Notes
2C | Ecosystem asset map | May 2025 | OWINN, GWDB | Complete asset map by _. |  | 
6C | Create dashboard | May 2025 | OWINN, GWDB | Complete dashboard by _. |  | 
2A | Outreach metrics | Sep 2025 | OWINN, GWDB,DETR, WC, NVWorks, DWSS | _ hires after job fair, _ clients placed in training after visiting job centers, etc. |  | 
2B | Cross promote workforce services to business agencies | Sep 2025 | OWINN, Dept. of Taxation, Secretary of State, DETR, Dept. of B&I | Develop consistent branding by _. |  | 
3B | Priority for small businesses | Sep 2025 | Nonprofits, DETR, Dept. of B&I, GOED, Secretary of State, OWINN, GWDB | Attend _ small business events. Partner with _ small business advocacy groups. |  | 
3C | Gap analysis | Sep 2025 | OWINN, GWDB | Complete gap analysis by _. Start stakeholder engagement by _. |  | 
5A | Enhance career opportunities for staff | Jun 2026 | State DHRM, OWINN, DETR, WC, NVWorks, DWSS, nonprofits | _ increase in case workers, etc. |  | 
4C | New programming | Jun 2026 | OWINN, GWDB, GOED, RDAs, NSHE, NDE, WC, NVWorks, CTE coordinators, training providers, nonprofits, Dept. of B&I, DETR | Analyze gap analysis and in-demand skills list by _. Convene work groups by _. |  | 

## Slide 14
Execution Teams + Rules of Engagement
13 | GWDB Strategic Plan
Begin with Action Items for Dec 2024 and Feb 2025
  3A – Application and referral system
  1B – “Did you know?” campaign
  1C – Workforce inventory
  1A – Shared calendar
  4A – Jobseekers asset map
  4B – In-Demand skills list
  5C – Data-sharing agreements for dashboard
Agencies will assign a point person for each Action Item’s Execution Team by July 31
Have initial members of the Execution Teams listed above meet before the next GWDB Full Board meeting on August 21
Purpose of the Execution Teams:
  Working across agencies to achieve common goal
  Breaking siloes
  Innovating traditional methods
  Collaboration and comradery
  What gets tracked gets done